## PROJECT CHARTER
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | AI Chatbot
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2023-08-31
EXPECTED COMPETION DATE | 2023-08-26
ESTIMATED COST | 0
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | To build a unified, speech-driven chatbot linked to multiple social media platforms for Cloud Counselage Pvt Ltd's Industry Academia Community Program, saving costs, and improving customer support efficiency.
BUSINESS CASE | Developing a unified chatbot will enhance customer support, reduce costs, and increase efficiency, benefiting Cloud Counselage Pvt Ltd's Industry Academia Community Program.
GOALS/METRICS | 1. Increase customer support cost savings by 30%. 2. Reduce average response time by 20%. 3. Achieve 90% accuracy in chatbot responses. 4. Serve 80% of user queries through speech-driven interactions. 5. Integrate with at least four social media platforms.
EXPECTED DELIVERABLES | 1. Functional and speech-driven unified chatbot application. 2. App demo video (5 mins) showcasing the chatbot's capabilities. 3. Complete source code and GitHub repository. 4. Comprehensive project documentation, including requirements, design, and test plans. 5. Installation & Operations Guide and Project Report summarizing the project's outcomes.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | 1. Building a speech and text driven Generative AI Chatbot. 2. Integration with Facebook, Instagram, LinkedIn, WhatsApp, and SMS. 3. Backend for storing FAQs and answers. 4. Speech-driven interactions. 5. Natural Language Processing for improved responses.
OUTSIDE OF SCOPE | 1. Developing a mobile app or website for the chatbot. 2. Integrating with other social media platforms not mentioned. 3. Advanced natural language understanding (NLU) capabilities. 4. Handling payment processing or sensitive data. 5. Providing live human customer support.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Snehil Sharma
SUPPORT RESOURCES | VSCode, Python, Flask, HTML, CSS, JavaScript, OpenAI API, ChimeraGPT API
COST ALLOCATION | 0
SPECIAL NEEDS | Google Cloud Platform (GCP) App Engine
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Harshada Topale
KEY STAKEHOLDERS | Harshada Topale
END CUSTOMERS | Cloud Counselage Pvt. Ltd.
EXPECTED BENEFIT | The expected benefit is to enhance student engagement and learning experience within the Industry Academia Community (IAC) Internship Program by providing prompt and accurate query resolution through the AI chatbot.
PROJECT RISKS, CONSTRAINTS AND ASSUMPTIONS
PROJECT RISK | 1. Inadequate NLP model performance. 2. Integration issues with social media platforms. 3. Speech recognition accuracy challenges. 4. Insufficient training data for the chatbot. 5. Security vulnerabilities and data breaches.
PROJECT CONSTRAINTS | 1. Sufficient resources and expertise for chatbot development. 2. Availability of FAQs and their accurate answers. 3. Social media APIs remain accessible and functional. 4. Adequate user engagement with the chatbot. 5. Speech recognition technology works effectively.
PROJECT ASSUMPTION | 1. Development must be done in Python. 2. Use of popular ML and DS libraries is allowed. 3. Adherence to standard code and output submission format. 4. The application should be of high quality and free from distractions. 5. Real-life scenarios should be considered for project features and outcomes. 6. All deliverables, including documentation, must be provided.