## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Snehil Sharma
Document Created On: | 2023-08-31
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT SCHEDULE
DOCUMENT VERSION: 1.0
PROJECT NAME | AI Chatbot
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Speech & Text driven Generative AI Chatbot
PROJECT SCOPE | The project scope involves developing an AI chatbot tailored for the Industry Academia Community (IAC) Internship Program, enabling instant query responses and efficient handling of student inquiries.
PROJECT START DATE | 2023-07-31
PROJECT END DATE | 2023-08-26
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | 1 Initiation | Team Lead | 2023-08-03 | 2023-08-06 | 4 | COMPLETED
| 1.1 Identify business problem |  | 2023-08-03 | 2023-08-04 | 2 | COMPLETED
| 1.2 Recruit a team |  | 2023-08-04 | 2023-08-05 | 2 | COMPLETED
| 1.3 Create a project charter |  | 2023-08-04 | 2023-08-05 | 2 | COMPLETED
| 1.4 Requirement gathering |  | 2023-08-05 | 2023-08-06 | 2 | COMPLETED
2 | 2 Planning | Team Lead | 2023-08-07 | 2023-08-10 | 4 | COMPLETED
| 2.1 Approval of business process |  | 2023-08-07 | 2023-08-08 | 2 | COMPLETED
| 2.2 Baseline project plan |  | 2023-08-08 | 2023-08-09 | 2 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2023-08-09 | 2023-08-10 | 2 | COMPLETED
3 | 3 Execution | Team Lead | 2023-08-11 | 2023-08-22 | 12 | COMPLETED
| 3.1 Design |  | 2023-08-11 | 2023-08-15 | 5 | COMPLETED
| 3.1.1 UI/UX Design |  | 2023-08-11 | 2023-08-13 | 3 | COMPLETED
| 3.1.1.1 Wireframe Creation |  | 2023-08-11 | 2023-08-12 | 2 | COMPLETED
| 3.1.1.2 UI Mockup Design |  | 2023-08-13 | 2023-08-13 | 1 | COMPLETED
| 3.1.2 System Architecture Design |  | 2023-08-14 | 2023-08-15 | 2 | COMPLETED
| 3.1.2.1 Determine Frontend-Backend Interaction |  | 2023-08-14 | 2023-08-14 | 1 | COMPLETED
| 3.1.2.2 Choose Technology Stack |  | 2023-08-15 | 2023-08-15 | 1 | COMPLETED
| 3.2 Development |  | 2023-08-16 | 2023-08-22 | 7 | COMPLETED
| 3.2.1 Frontend Development |  | 2023-08-16 | 2023-08-17 | 2 | COMPLETED
| 3.2.1.1 Set Up Chat Interface |  | 2023-08-16 | 2023-08-16 | 1 | COMPLETED
| 3.2.1.2 Implement Voice Input |  | 2023-08-17 | 2023-08-17 | 1 | COMPLETED
| 3.2.2 System Architecture Design |  | 2023-08-18 | 2023-08-21 | 4 | COMPLETED
| 3.2.2.1 PDF Text Extraction |  | 2023-08-18 | 2023-08-18 | 1 | COMPLETED
| 3.2.2.2 OpenAI Integration |  | 2023-08-18 | 2023-08-20 | 3 | COMPLETED
| 3.2.2.3 ChimeraGPT API Integration (For OpenAI) |  | 2023-08-18 | 2023-08-20 | 3 | COMPLETED
| 3.2.2.4 Speech Recognition Integration |  | 2023-08-21 | 2023-08-22 | 2 | COMPLETED
| 3.3 Testing |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.1 Unit Testing |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.1.1 Test PDF Extraction |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.1.2 Test OpenAI Model Integration |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.1.3 Test ChimeraGPT Integration |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.1.4 Test Speech Recognition |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.2 Integration Testing |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.2.1 Test End-to-End Functionality |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.3.2.2 Validate UI/UX |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
| 3.4 Deployment and Go-Live |  | 2023-08-24 | 2023-08-24 | 1 | COMPLETED
| 3.4.1 Set Up Hosting Environment |  | 2023-08-24 | 2023-08-24 | 1 | COMPLETED
| 3.4.2 Deploy Frontend and Backend |  | 2023-08-24 | 2023-08-24 | 1 | COMPLETED
| 3.4.3 Final System Checks |  | 2023-08-24 | 2023-08-24 | 1 | COMPLETED
3.4.4 Launch the Chatbot to Production
4 | 4 Closure | Team Lead | 2023-08-26 | 2023-08-26 | 1 | COMPLETED
| 4.1 Project Review and Lessons Learned |  | 2023-08-26 | 2023-08-26 | 1 | COMPLETED
| 4.2 Handover to Cloud Counselage Pvt. Ltd. |  | 2023-08-26 | 2023-08-26 | 1 | COMPLETED