## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Project title: | AI Chatbot |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | Issue | 6 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2023-08-23 | Project Team Lead: | Snehil Sharma |  |  | Dependency | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 13 |  |  |  |  | #VALUE!
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Chatbot model may generate inaccurate responses | Users may receive incorrect information | Regular model training and validation | Project Team Lead | Critical | 250 | Closed | Risk
2 | Risk | PDF (For FAQs) extraction failure | Unable to read PDF content | Improve PDF extraction code | Project Team Lead | High | 200 | Closed | Assumption
3 | Risk | Integration issues with social media platforms | Delays in communication | Regular monitoring and troubleshooting | Project Team Lead | High | 200 | Closed | Issue
4 | Risk | PDF (For FAQs) content quality | Inaccurate or incomplete information | Review and improve PDF content | Project Team Lead | Moderate | 150 | Closed | Dependency
5 | Issue | Backend stability | Server crashes under heavy load | Optimize server resources | Project Team Lead | Critical | — | Closed
6 | Issue | Unforeseen bugs in chatbot logic | Chatbot may give unexpected responses | Extensive testing and bug fixing | Project Team Lead | Critical | — | Closed | Open
7 | Issue | Speech recognition | Recognition errors | Investigate and improve speech recognition | Project Team Lead | High | — | Closed | Closed
8 | Issue | Performance degradation during high traffic | Chatbot responses may slow down | Monitor server load and optimize code | Project Team Lead | High | — | Closed
9 | Issue | UI responsiveness | Laggy UI during interactions | Optimize frontend code | Project Team Lead | Moderate | — | Closed | Critical
10 | Issue | User input handling | Unable to handle special characters | Implement input sanitization | Project Team Lead | Low | — | Closed | High
11 | Assumption | PDF content extraction accuracy | Incorrect information | Double-check extraction process | Project Team Lead | Moderate | — | Closed | Moderate
12 | Assumption | Reliable internet connection for speech recognition | Speech recognition may fail with poor network | Provide fallback options for text input | Project Team Lead | Moderate | — | Closed | Low
13 | Assumption | User familiarity with chatbot interfaces | Users may struggle to interact with the chatbot | Provide clear instructions and help messages | Project Team Lead | Low | — | Closed | Negligible
14 | Dependency | OpenAI API limitations | Slow response times | Explore caching mechanisms | Project Team Lead | Low | — | Closed