## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Artificial Intelligence
INTERN NAME: | Snehil Sharma
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2023-08-11
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | AI Chatbot
INTERN NAME | Snehil Sharma
PROJECT MANAGER | Harshada Topale
INTRODUCTION
Test Strategies: The testing phase of the AI chatbot project aims to ensure the accuracy, reliability, and seamless functionality of the chatbot across various platforms and user interactions. The strategies employed focus on platform integration, accuracy validation, user experience, API reliability, error handling, performance, and more. Test Process: The testing process is iterative and comprises various stages, including test planning, test case creation, test execution, and results analysis. The process involves simulating user interactions, evaluating chatbot responses, identifying discrepancies, and iterating to refine the chatbot's performance. Workflow: 1. Requirement Analysis: Understanding the project requirements and objectives, including platform integration and user engagement expectations. 2. Test Planning: Defining the scope, objectives, test scenarios, and test cases based on different use cases. 3. Test Case Creation: Developing detailed test cases that cover a range of scenarios, including platform-specific interactions and user inputs. 4. Test Execution: Running test cases to validate chatbot responses, assess accuracy, test speech recognition, check UI consistency, API integration, and more. 5. Results Analysis: Comparing actual outcomes with expected results, identifying discrepancies, and categorizing issues. 6. Issue Reporting: Documenting and reporting identified issues, whether related to responses, UI, integration, or performance. 7. Issue Resolution: Collaborating with the development team to address identified issues, including correcting responses, optimizing UI, and improving performance. 8. Regression Testing: Repeating tests after issue resolution to ensure that fixes do not introduce new problems. 9. User Acceptance Testing: Involving real users to validate the chatbot's functionality and gather feedback. Methodologies: 1. Agile Methodology: The project follows an agile approach, allowing for flexibility and iterative development. Testing is integrated throughout the development cycle, ensuring quick feedback loops and continuous improvement. 2. Test-Driven Development (TDD): TDD principles guide test case creation before implementing chatbot features. Tests validate the intended functionality. 3. Continuous Integration and Continuous Deployment (CI/CD): Automated testing is integrated into the CI/CD pipeline to catch issues early and ensure consistent quality across deployments. 4. User-Centric Approach: User feedback and acceptance testing play a crucial role in validating the chatbot's effectiveness and alignment with user needs.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
1. Platform Integration Testing: Testing the chatbot's functionality and responses on Facebook, Instagram, LinkedIn, Twitter, YouTube, Email, and the website. 2. Multi-Platform UI Testing: Ensuring consistent user interface and experience across different devices and platforms. 3. Accuracy and Reliability Testing: Verifying the accuracy of chatbot responses and their alignment with predefined answers. 4. Speech Recognition Testing: Validating the chatbot's ability to accurately recognize and convert speech input into text. 5. API Integration Testing: Testing the integration with OpenAI API for generating accurate responses. 6. Error Handling Testing: Verifying the chatbot's ability to handle and communicate errors to users. 7. Performance and Load Testing: Evaluating the chatbot's performance under various user loads and interactions. 8. User Acceptance Testing (UAT): Involving real users to validate the chatbot's functionality and gather feedback. 9. Cross-Browser Compatibility Testing: Verifying the chatbot's performance and appearance on different web browsers.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
1. Advanced NLP Algorithms: Deep analysis of the Natural Language Processing algorithms or their enhancement is out of scope. 2. Full Conversational AI Development: Building a complex conversational AI system with context and memory is not included. 3. Integration with Other AI Models: Integrating additional AI models beyond GPT-3.5 is not part of the current scope. 4. Customization for Each User: Creating highly personalized responses for individual users based on historical interactions is not included. 5. Long-Term Learning: Continuous learning from user interactions to adapt the chatbot over time is not in scope. 6. Voice Synthesis Testing: Testing the chatbot's ability to synthesize voice responses is not within the current scope. 7. Localization Testing: Testing the chatbot's responses in different languages or cultures is not included. 8. Third-Party Services Testing: Testing third-party services beyond OpenAI & ChimeraGPT API, such as social media APIs, is not part of scope.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
• Ensure the AI chatbot application delivers an optimal user experience by providing accurate, relevant, and coherent responses across multiple platforms and interactions. • Validate that the chatbot conforms to both functional and non-functional requirements, ensuring consistent and reliable performance in addressing user queries. • Align with the quality specifications defined by the client to enhance user engagement and customer satisfaction within Cloud Counselage Pvt Ltd's Industry Academia Community Program. • Thoroughly test the application to identify and rectify any deviations from predefined answers, enhancing the value of information provided to users. • Proactively identify and address bugs or issues during testing to ensure a smooth and error-free user experience upon deployment. • Exceed user expectations by delivering a chatbot solution that contributes to the success of the Industry Academia Community Program while meeting high-quality standards.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst (Snehil Sharma): • Develop comprehensive test plans, cases, and scripts for chatbot functionality validation. • Execute integration, functional, UI, speech recognition, accuracy, and performance testing. • Identify defects, track resolutions, and collaborate with developers. • Conduct user acceptance testing (UAT) for feedback and validation. Test Manager (Snehil Sharma): • Oversee testing, ensure adherence to standards and schedules. • Plan, assign tasks, and monitor progress. • Review and approve testing documents. Configuration Manager (Snehil Sharma): • Manage version control and configuration. • Track changes, collaborate with developers. • Maintain organized code repository. Developer (Snehil Sharma): • Design and develop chatbot features. • Collaborate with QA, adhere to coding standards. • Address defects, provide testing support. Installation Team (Snehil Sharma): • Collaborate with QA for deployment preparation. • Install the require things and configure chatbot. • Validate post-installation functionality.
TEST METHODOLOGY
OVERVIEW
The project employs Agile methodology for testing due to its flexibility and iterative nature. Agile was chosen to accommodate changing requirements, facilitate continuous feedback, and ensure incremental development. This approach promotes early defect detection, collaboration, and user involvement. Agile's adaptability aligns with the evolving AI chatbot landscape, allowing for timely deliverables and effective responses to changes. By embracing Agile, the project ensures a user-centric, dynamic testing approach that contributes to the success of Cloud Counselage Pvt Ltd's Industry Academia Community Program.
TEST LEVELS
Considering the scope, timelines, and objectives of the project, the chosen test level is "System Testing". System Testing involves evaluating the complete and integrated application as a whole to ensure that it meets the desired quality standards and functions as expected across all its components and interactions. Given the complexity and multi-platform nature of the AI chatbot, System Testing is well-suited to validate its overall functionality and user experience. System Testing: • Objective: To verify the end-to-end functionality and behavior of the AI chatbot application across multiple platforms and interactions. • Scope: The entire application, including its integration with Facebook, Instagram, LinkedIn, Twitter, YouTube, Email, and the website. • Testing Focus: • Platform Integration: Validate smooth operation on various platforms. • Response Accuracy: Ensure accurate and coherent chatbot responses. • UI Consistency: Verify uniform user interface appearance. • Speech Recognition: Validate speech-to-text conversion accuracy. • API Integration: Test communication with OpenAI API. • Error Handling: Validate response to unexpected inputs and errors. • Performance: Evaluate response time and scalability under load. • Test Cases: Comprehensive test cases covering various user scenarios and platform interactions. • Test Execution: Simulate real-world interactions to validate the end-to-end functionality. • Expected Outcome: Identification of defects, validation of responses, and assurance of quality. • Benefits: Ensures the application functions seamlessly across all platforms and provides accurate responses to users.
BUG TRIAGE
Bug 1: Speech Recognition Inaccuracy • Severity: High • Impact: Chatbot misinterprets speech inputs, providing incorrect responses. • Resolution: Investigate and fine-tune speech recognition algorithms. • Priority: Critical • Schedule: Immediate attention and resolution. Bug 2: Slow Response Time under High Load • Severity: Medium • Impact: Chatbot response time increases significantly during peak usage. • Resolution: Performance optimization and load testing. • Priority: High • Schedule: Address in the upcoming development cycle. Bug 3: UI Inconsistency on Mobile Devices • Severity: Medium • Impact: Users experience layout issues on mobile devices. • Resolution: CSS adjustments to ensure responsive design. • Priority: High • Schedule: Fix in the next development iteration. Bug 4: Unhandled ChimeraGPT API Error Messages • Severity: Low • Impact: Users encounter unhandled error messages from the ChimeraGPT API. • Resolution: Implement error handling to display user-friendly error messages. • Priority: Medium • Schedule: Fix in the next development iteration.
TEST COMPLETENESS
1. 100% Test Coverage: Ensure that all functional and non-functional aspects of the AI chatbot application are thoroughly tested. This includes platform integration, UI, speech recognition, accuracy, performance, and error handling. 2. Execution of All Manual and Automated Test Cases: Execute all planned manual and automated test cases to validate the chatbot's behavior across different scenarios, platforms, and interactions. This involves testing both positive and negative test cases. 3. Bug Resolution: Ensure that all identified bugs are addressed, fixed, and verified. Bugs should be retested to confirm their resolution, and a retest strategy should be applied to validate the fixes. 4. Test Case Validation: Confirm that all test cases have been executed, and their results have been documented accurately. This includes updating the status of test cases based on their execution outcomes. 5. Functional and Non-Functional Validation: Ensure that both functional and non-functional requirements have been validated through testing. Functional validation involves confirming that the chatbot behaves as expected, while non-functional validation includes performance, responsiveness, and accuracy checks. 6. Regression Testing: Perform thorough regression testing to ensure that new code changes, bug fixes, and enhancements do not introduce new defects or negatively impact existing functionality. 7. Documentation: Update testing documentation, including test plans, test cases, test results, and bug reports. Maintain accurate records of testing activities and outcomes. 8. Alignment with Exit Criteria: Ensure exit criteria are met, including test coverage, bug resolution, and user satisfaction, indicating application readiness for deployment.
TEST DELIVERABLES
1. Test Plan: Document outlining the testing scope, objectives, strategies, resources, and schedules. 2. Test Cases: Comprehensive set of manual and automated test cases covering various scenarios and interactions. 3. Requirement Traceability Matrix (RTM): Matrix linking test cases to specific requirements, ensuring comprehensive coverage. 4. Bug Reports: Detailed reports documenting identified defects, including steps to reproduce, severity, and impact. 5. Test Strategy: Document describing the chosen test approach, methodologies, levels, and techniques. 6. Test Metrics: Metrics showcasing testing progress, coverage, defect density, and other relevant measures. 7. Test Summary Report: Compilation of testing activities, results, bug statistics, and lessons learned. 8. Resource and Environment needs: Document describing Testing tools and environment.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
1. Requirements Tracking Tool: • Tool: Jira • Purpose: Manage and track project requirements, user stories, and test cases. 2. Bug Tracking Tool: • Tool: Jira • Purpose: Log, track, and manage identified defects, ensuring timely resolution. 3. Automation Tools: • Selenium: Automated UI testing across multiple platforms. • Cypress: Performed end-to-end testing with a focus on modern web applications. • Postman: Automated API testing and integration validations. • Appium: Automated mobile application testing across different devices. 4. Performance Testing Tool: • JMeter: Perform load, stress, and performance testing to assess application responsiveness. 5. Code Review and Version Control Tool: • GitHub: Collaborate on code, manage versions, and review code changes. 6. Speech Recognition Validation & Browser Compatibility Testing Tool: • Browser DevTools: Inspect speech recognition responses for accuracy and consistency. • BrowserStack: Test the chatbot across various browsers and devices for compatibility. 7. Test Management Tool: • TestRail: Manage test cases, execute tests, and generate comprehensive reports.
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Minimum Hardware Requirements: • Processor: Intel Core i3 or equivalent • RAM: 4 GB • Storage: 10 GB available space • Internet Connection: Broadband or Wi-Fi connectivity Software Requirements: • Operating System: Windows 7 and above, Linux, Mac • Office Suite: Office 2013 and above (for documentation and communication) • Browsers: Chrome, Firefox, Safari, Edge (for cross-browser testing) • Speech Recognition Support: Browser with speech recognition support (for testing speech-driven features) • API: OpenAI & ChimeraGPT (for generative AI response) • API Testing: Postman (for API validation) • Test Management Tool: TestRail (for managing test cases and execution) Additional Client-Specific Software: • MS Exchange is required for integration and communication.
ADDITIONAL COMMENTS
1. As part of the test plan, thorough test coverage has been ensured across various dimensions of the AI chatbot application. This includes platform integration testing to validate seamless performance on different social media platforms such as Facebook, Instagram, LinkedIn, Twitter, and YouTube. 2. Special emphasis is being placed on the accuracy and reliability of the speech recognition feature. Testing scenarios are designed to encompass diverse accents and languages, ensuring robustness in real-world user interactions. 3. For API integration testing, extensive validation of communication with the OpenAI and ChimeraGPT API is being conducted. This encompasses API calls, handling of responses, and adherence to OpenAI guidelines for secure integration. 4. The test plan also accounts for different user scenarios, error handling, and regression testing. Focus is given to user acceptance testing (UAT) where real users will provide valuable feedback, shaping the application's user experience. 5. Documentation review is ongoing to ensure that all testing activities are well-documented, providing transparency and clarity to stakeholders and team members. 6. Regular code review and integration efforts are in progress to ensure that code changes are well-managed and contribute to the overall quality of the application. 7. The deployment testing phase will validate the deployment process, ensuring that the AI chatbot can be smoothly deployed to various platforms as intended.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
UI Consistency | Verify uniform UI appearance across platforms | 12.08.2023 | 15.08.2023 | Team Lead | PASSED | CSS adjustments
Speech Recognition Accuracy | Test accuracy of speech recognition feature | 14.08.2023 | 18.08.2023 | Team Lead | PASSED | —
API Integration | Validate communication with OpenAI & ChimeraGPT API | 16.08.2023 | 20.08.2023 | Team Lead | PASSED | —
Performance Testing | Assess response time under high load | 18.08.2023 | 21.08.2023 | Team Lead | PASSED | Load testing
Error Handling | Verify chatbot response to unexpected inputs | 20.08.2023 | 23.08.2023 | Team Lead | PASSED | —
Bug Verification | Retest resolved bugs to confirm fixes | 11.08.2023 | 14.08.2023 | Team Lead | PASSED | —
Regression Testing | Ensure no new defects are introduced | 13.08.2023 | 17.08.2023 | Team Lead | PASSED | —
Documentation Review | Review and update testing documentation | 15.08.2023 | 19.08.2023 | Team Lead | PASSED | —
Code Review and Integration | Collaborate on code changes and integration | 17.08.2023 | 22.08.2023 | Team Lead | PASSED | —
Platform Integration | Validate chatbot behavior on different browsers. | 19.08.2023 | 23.08.2023 | Team Lead | PASSED | —